## BOQ
BILL OF QUANTITIES (BOQ)
Project: Shree Balaji Residency, Block B ¦ Contractor: M/s Verma Constructions ¦ Agreement No. SBR/2026/014 ¦ Date: 15-Mar-2026
Item | Description | Unit | BOQ Qty | Rate (INR) | Amount (INR) | GST %
1 | Earthwork excavation in foundation | m3 | 500 | 180 | 90000 | 18%
2 | PCC 1:4:8 in foundation | m3 | 60 | 4800 | 288000 | 18%
3 | RCC M25 in footings & columns | m3 | 120 | 7200 | 864000 | 18%
4 | Steel reinforcement Fe500 | MT | 40 | 78000 | 3120000 | 18%
5 | Brickwork 230 mm in CM 1:6 | m2 | 2000 | 950 | 1900000 | 18%
6 | Internal plaster 12 mm | m2 | 4500 | 210 | 945000 | 18%
7 | External plaster 18 mm | m2 | 2800 | 260 | 728000 | 18%
8 | Vitrified tile flooring 600x600 | m2 | 1800 | 1150 | 2070000 | 18%
9 | Terrace waterproofing (membrane) | m2 | 600 | 480 | 288000 | 18%
10 | Aluminium sliding windows | m2 | 350 | 4200 | 1470000 | 18%
11 | Flush doors incl. frame & fittings | Nos | 80 | 6500 | 520000 | 18%
12 | Interior painting, 2 coats emulsion | m2 | 6000 | 95 | 570000 | 18%
13 | Electrical wiring points (concealed) | Nos | 750 | 850 | 637500 | 18%
14 | CPVC water supply piping | m | 1200 | 320 | 384000 | 18%
15 | Supply of OPC 43 grade cement | Bags | 2500 | 380 | 950000 | 28%
| TOTAL (excl. GST) |  |  |  | 14824500

## RA Bill 1
RUNNING ACCOUNT BILL — RA BILL No. 1
Project: Shree Balaji Residency, Block B ¦ Contractor: M/s Verma Constructions ¦ Bill Date: 31-Mar-2026
Item | Description | Unit | BOQ Rate | Cum. Qty (prev.) | Cum. Qty (to date) | Qty This Bill | Rate Charged | Amount (INR) | GST % | GST Amt (INR) | Line Total (INR)
1 | Earthwork excavation in foundation | m3 | 180 | 0 | 200 | 200 | 180 | 36000 | 18% | 6480 | 42480
2 | PCC 1:4:8 in foundation | m3 | 4800 | 0 | 40 | 40 | 4800 | 192000 | 18% | 34560 | 226560
3 | RCC M25 in footings & columns | m3 | 7200 | 0 | 50 | 50 | 7200 | 360000 | 18% | 64800 | 424800
4 | Steel reinforcement Fe500 | MT | 78000 | 0 | 15 | 15 | 78000 | 1170000 | 28% | 327600 | 1497600
15 | Supply of OPC 43 grade cement | Bags | 380 | 0 | 800 | 800 | 380 | 304000 | 28% | 85120 | 389120
| BILL TOTAL | [6 empty] | 2062000 |  | 518560 | 2580560
Certified by Site Engineer. Measurement Book Ref: MB-01/2026.

## RA Bill 2
RUNNING ACCOUNT BILL — RA BILL No. 2
Project: Shree Balaji Residency, Block B ¦ Contractor: M/s Verma Constructions ¦ Bill Date: 30-Apr-2026
Item | Description | Unit | BOQ Rate | Cum. Qty (prev.) | Cum. Qty (to date) | Qty This Bill | Rate Charged | Amount (INR) | GST % | GST Amt (INR) | Line Total (INR)
1 | Earthwork excavation in foundation | m3 | 180 | 200 | 450 | 250 | 180 | 45000 | 18% | 8100 | 53100
3 | RCC M25 in footings & columns | m3 | 7200 | 50 | 110 | 60 | 7200 | 432000 | 18% | 77760 | 509760
4 | Steel reinforcement Fe500 | MT | 78000 | 15 | 28 | 13 | 78000 | 1014000 | 18% | 182520 | 1196520
5 | Brickwork 230 mm in CM 1:6 | m2 | 950 | 0 | 500 | 500 | 995 | 497500 | 18% | 89550 | 587050
15 | Supply of OPC 43 grade cement | Bags | 380 | 800 | 1500 | 700 | 380 | 266000 | 28% | 74480 | 340480
| BILL TOTAL | [6 empty] | 2254500 |  | 432410 | 2686910
Certified by Site Engineer. Measurement Book Ref: MB-02/2026.

## RA Bill 3
RUNNING ACCOUNT BILL — RA BILL No. 3
Project: Shree Balaji Residency, Block B ¦ Contractor: M/s Verma Constructions ¦ Bill Date: 31-May-2026
Item | Description | Unit | BOQ Rate | Cum. Qty (prev.) | Cum. Qty (to date) | Qty This Bill | Rate Charged | Amount (INR) | GST % | GST Amt (INR) | Line Total (INR)
1 | Earthwork excavation in foundation | m3 | 180 | 200 | 500 | 300 | 180 | 54000 | 18% | 9720 | 63720
3 | RCC M25 in footings & columns | m3 | 7200 | 110 | 120 | 10 | 7200 | 72000 | 18% | 12960 | 84960
5 | Brickwork 230 mm in CM 1:6 | m2 | 950 | 500 | 1200 | 700 | 950 | 665000 | 18% | 119700 | 784700
6 | Internal plaster 12 mm | m2 | 210 | 0 | 800 | 800 | 210 | 168000 | 18% | 30240 | 198240
| BILL TOTAL | [6 empty] | 959000 |  | 172620 | 1131620
Certified by Site Engineer. Measurement Book Ref: MB-03/2026.

## ANSWER KEY (internal)
PLANTED ERRORS — TEAM REFERENCE ONLY (do not show in demo)
# | Location | Error type | Detail | Financial impact
E1 | RA Bill 1, Item 4 (Steel) | Wrong GST rate | Steel reinforcement charged 28% GST; correct rate is 18%. Excess GST on 15 MT x 78,000 = 11,70,000 base. | Excess GST = 11,70,000 x 10% = INR 1,17,000
E2 | RA Bill 2, Item 5 (Brickwork) | Rate drift vs BOQ | Rate charged 995/m2 vs BOQ rate 950/m2 on 500 m2 billed. | Overcharge = 500 x 45 = INR 22,500 + 18% GST 4,050 = INR 26,550
E3 | RA Bill 3, Item 1 (Excavation) | Cross-bill double-billing | Cum. Qty (prev.) shown as 200 m3 but RA Bill 2 already certified cumulative 450 m3. Bill charges 300 m3 instead of 50 m3 -> 250 m3 double-billed. | Overcharge = 250 x 180 = INR 45,000 + 18% GST 8,100 = INR 53,100
|  |  | TOTAL LEAKAGE ACROSS 3 BILLS | INR 1,96,650